## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the process and include a detailed description of every step. Add reasoning on why you took certain decisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description | Bonus
Briefing | 0.5 | 2022-05-17 | Carefully reading the instructions of the assignment
Ground maze | 1 | 2022-05-18 | Finding a good way to generate the ground of the maze. In the end I decided to make a prefab of a plane of 1x1 and call that a cell. Then I wrote a script that configured the number of cells instantiated and made it configurable in height and width of the whole ground in the inspector. Later on I can use those values to communicate with the UI. For sure there is a more efficient way of doing this, but for now it works.
Designing walls | 0.5 | 2022-05-18 | A designed very simple walls with a nice material in Blender. Later I need to figure out how to write the actual algoritmn to make the maze.
Research algoritmn | 2 | 2022-05-20 | Trying to get a deeper understanding of the algoritmn. Writing the actual algoritmn. I used some ideas of the wikipedia page mentioned in the instructions of this assesment. I am creating probably a quite unorthodox method with a lot of lists and some loops. I chose not to follow a tutorial because the danger emerges you just copy that code and I don't show enough what I can do.
Detecting neighbours cells | 3 | 2022-05-24 | I made the GameManager script detect what cells are at the border and where at the border (left, right, up or down). I put them also in a list and those lists help me determine the neighbours of a particular cell. A cell in the center of the maze has neighbours up and down that can be determined with their uniqueID (I gave all cells a number starting from 0 to the number of cells generated) minus the width, and plus the width. The neighbours left and right are simply the uniqueID + 1 and - 1. Then I checked if the particular cell is in the lists mentioned above because than the neighbours are different. In the cornerleft for example the neighbours are uniqueID + 1 and uniqueID + width. I determined these neighbours with if-statements.
Visual Representation | 3 | 2022-05-24 | I created a Sphere called visual representation. The idea is that this Sphere will go to random cells in a gridbased path. So I set a random target cell and the visual representation is going there and along the way it is removing walls. I will try to remove walls with EnterTriggerCollider. Every step it is determining what of the four neighbour cells is closer to the goal. If there are two cells the same distance, it will chose a random cell out of these two.
Arch | 1 | 2022-05-24 | I created an Arch with Blender. I make it spawn at the opening that is randomly created by the algoritmn. | X
Final touches | 6 | 2022-05-24 | I succeeded in making walls disappear by the EnterTrigger of the visual representation. I played a bit with the maximum amount of walls per cell that should be destroyed. I almost got the system running but sometimes (in like 20% of the cases) I still generate some unaccesible areas. I don't know how to fix that for now.
Fixing bugs | 2 | 2022-05-24 | I had some bugs. If I generated from the UI, the maze was not correctly constructed. I fixed it.
Total amount of hours | 17